## To do list
Items | Survey | Assignee | Status | Urgency | Date | notes
Fill out pre-survey questionnaire on qualtrics | Retention | Nam | Complete |  |  |  | FALSE | FALSE
Create 8 test cases | Part 1 | Nam | Complete
Write down method for randomization | Part 1 & Rentention & Part 2 | Nam | Complete
Figure out how to publish the surveys | Part 1 & Rentention & Part 2 | Nam | Complete
Type out Canadian Cities in Survey Part 2 | Part 2 | Nam | Complete
Check tons vs tonnes | Part 2 | Nam | Complete
Identify cities that fall within a certain location | Part 1 | Nam | Complete |  |  | Complete for USA cities
Change carbon tax messaging - tax will be deducted... | Part 2 | Nam | Complete
Migrate Part 2 answers to piped text | Part 2 | Nam | Complete
Fix Carbon Calculator Code for new emissions | Part 1 | Nam | Complete
Fix introductory text display emissions | Part 1 | Nam | Complete |  |  | Intro text not displaying user's GHG but displays in chart
Fix bug when no vehicle is selected | Part 1 | Nam | Complete |  |  | When user selects No Vehicle, NaN appears
MAKE SURE TO EDIT TEXT ABOUT HEARING PROPERLY IN PROLIFIC | Part 1 | Nam | Complete |  |  | Configurable in Prolific - Dec 29, 2025: No need for this as we aren't doing any videos
Add part 3 in experience | Part 1 | Nam | Complete
Find out cities are below -1c | Part 1 | Nam | Complete |  |  | add option in survey that includes: proportioned heat pump vs gas, heat pump vs electric backup
reach out to Qualtrics re styling (Likert doubles, font size) | Part 1 | Nam | Complete |  |  | Dec 29, 2025: Source of formatting issues is from custom CSS. Dec 30, 2025: Fixed CSS with help from chatGPT
Get rid of question 29 b | Part 1 | Nam | Complete |  |  | Only get rid of b
PLAY AROUND WITH MOBILE EXPERIENCE | Part 1 & Rentention & Part 2 | Nam | Complete |  |  | Dec 30, 2025: Pretty much can't use mobile because HTML isn't optimized.
Check for currency in US/CAN in Survey Part 2 | Part 2 | Nam | Complete
Make changes to fuel type radiobuttons | Part 1 | Nam | Complete |  |  | Add plug-in hybrid option
Implement no vehicle radio buttons | Part 1 | Nam | Complete |  |  | Dec 31, 2025: Use 19,952 km for average distance
Revise vehicle emissions | Part 1 | Nam | Complete |  |  | Dec 31, 2025: I double checked the vehicle emissions and realized they were in kg/mile instead of kg/km. I have now fixed in the file, "footprint parameters". You could change numbers to new ones or divide by 1.609 (kms per mile) in the calculator.
Round values | Part 1 | Nam | Complete |  |  | Dec 31, 2025: Round the values for the carbon calculator to one decimal.
Check flight examples in survey | Part 1 | Nam | Complete |  |  | current examples for 1 t of flight CO2 emissions in Q32 (part 1) are Vancouver-Toronto and Chicago-NYC. Chek that these are based on the same calculator we use for Part 2, and if not find other examples based on the current calculator. Jan 6, 2026: Vancouver to Toronto - 1.3t, Chicago-NYC - .6t but Salt Lake city to NYC is 1.1 t
Make latest changes in Survey 1 | Part 1 | Nam | Complete |  |  | Note I have updated global per capita emissions to 4.8
Bold personal emissions | Part 1 | Nam | Complete |  |  | Bold the personal emissions html
Attach references document | Part 1 | Nam | Complete |  |  | Attach the references document for the html. https://www.dropbox.com/scl/fi/vwx4d781vmose1t433tgk/calculation-details.docx?rlkey=cxa64ktlv7mrc1xm43koew0rb&st=ytc42muo&dl=0
Get rid of Your emissions: for question 39 | Part 1 | Nam | Complete |  |  | For question 39, get rid of the Your emissions text at the top.
Error message | Part 1 | Nam | Complete |  |  | The number shouldn't be just higher vs lower.
find a new source for heating efficiency weights and update them. | Part 1 | Vivian | Complete
Make sure to have spendable money with Prolific | Part 1 & Rentention & Part 2 | Vivian | Complete |  |  | should be processed Weds Oct 27
Fill in Research Number in agreement | Part 1 & Rentention & Part 2 | Vivian | Complete
Find new carbon parameters | Part 1 | Vivian | Complete |  |  | note that some units have changed, I think the calculations will be the same though
write instructions re cold cities | Part 1 | Vivian | Complete |  |  | We won't bother with the back-up heat source distinction after all
review survey Part 1 | Part 1 | Vivian | Complete |  |  | CURRENT Dec 29 version - to discuss Friday Jan 2
modify instructions for Q41-Q44 to make clear what to do | Part 1 | Vivian | Complete
Finalize image - try nano banana pro | Part 1 | Vivian & Nam | Complete |  |  | Dec 29, 2025: Nam to add in final images
Sort out randomization | All | Vivian & Nam | Complete |  |  | Dec 29, 2025: finalize with Nick how to randomization participants. Nam to implement in Qualtrics
For most of those miles/km, how many people are in your vehicle | Part 1 | Nam | Complete |  |  | Add a question that asks how many passengers someone has when they drive
add number of people in car question into survey | Part 1 | Nam | Complete
Fix bugs in calculator | Part 1 | Nam | Complete | High |  | I said I drove hybrid truck and it didn’t count that mileage. Vehicle radio button was blank. Miles showed up when I toggled buttons. Also couldn't get past numerical checks for specific changes (first one: flight)
Revise global current emissions to same categories we use | Part 1 | Vivian | Complete
Fix error message for incorrect values, i.e., %1 | Part 1 | Nam | Complete |  |  | Your answer is off by at least 0.5 t. Please go back and correct it
Fix the answer order for flights (Yes, then No) | Part 1 | Nam | Complete |  |  | I plan to fly in 2026 goes first, then no I don't plan to fly.
revise order in graph and add diesel (same order in question): gas / diesel / hybrid / plug-in hybrid / electric. Change to "gas" in question. | Part 1 | Nam | Complete
Write explanation of calculation | Part 1 | Vivian | Complete |  |  | This is for the references document
Change example destinations | Part 1 | Nam | Complete |  |  | Dec 29, 2025: Add the rest of the longhaul flight images subject to Vivian's approvals. Jan 20, 2026 - Have Vivian check out maps before adding distances Jan 21, 2026 -
Top of y axis: current footprint BUT, use gas car, heat home w oil, eat omnivore, +1 long-haul flight | part 1 | Nam | Complete |  |  | This is for the graph size Jan 13, 2026: play around with parameters such as the ones we use in the survey aka 1 extra flight, could also try gas fueled car (not the sum, just the max)
Make a validation checklist | All | Nam | Complete |  |  | Dec 29, 2025: This is a checklist of all validation steps to be performed i.e., making sure that users enter a number, the number has be greater than 0, etc.
Fix excel to do list interface | All | Nam | Complete |  |  | Add a filter and calendar
Use Power Automate to Ingest emails into excel | All | Nam | Complete |  |  | Jan 20, 2026 - tested a flow out by extracting email contents
Change reelvant efficiency factors | Part 1 | Nam | Complete
Update vehicle emissions code | Part 1 | Nam | Complete
Change number of per capita emissions | Part 1 | Nam | Complete
Implement number of passengers per vehicle question | Part 1 | Nam | Complete
Demo ChatGPT Agent for average distances | Part 1 | Nam | Complete
Type out Part 2 questions using contact list | Part 2 | Nam | Complete
Change per capita emissions | Part 1 | Nam | Complete
find out average emissions for short, medium and long haul North American flights | Part 1 | Nam | Complete |  |  | Jan 21, 2026 - Calculate and comment in documentation & add to calculator (code)
Make the graph smaller | Part 1 | Nam | Complete |  |  | Try to make the graph fit on one page
Change flight maps for new distances | Part 1 | Nam | Complete
Change dis
Change flight questions to reflect new radii | Part 1 | Nam | Complete |  |  | new bounds for short, medium and long haul
Filling out part 2 survey questions using piped text | Part 2 | Nam | Complete
Scaffold part 2 questions | Part 2 | Nam | Complete |  |  | Try copy and pasting the blocks and make sure that they share the same characteristics
Long distance maps | Part 1 | Nam | Complete
Insert code for grahs | Part 1 | Nam | Complete
Code the y-axis to the user's original emission + 3 + 1
Change global average after doing research on it | Part 1 | Vivian & Nam | Complete
Question 41 | Part 1 | Nam | Complete |  |  | set embedded value for their flight emission : GHG_Total - flight_emissions - 0.5; GHG_Total - flight_emissions + 0.5
Question 42a | Part 1 | Nam | Complete |  |  | current_emissions - current_vehicle_emissions + emissions/km w EV (in their jurisdiction) * [KMs/Miles]
|  | Nam | Complete |  |  | current_emissions - current_vehicle_emissions + (difference in emissions/km w current car vs EV)* [KMs/Miles]
Question 42b |  | Nam | Complete |  |  | current_emissions + (gas_car_emsssions/km)* [average KMs/Miles]
Question 42c | Part 1 | Nam | Complete |  |  | current_emissions - current_vehicle_emissions + emissions/km w gas * [KMs/Miles]
Question 43 |  | Nam | Complete |  |  | current_emissions - (current_diet_emissions + vegan_diet_emissions)
Question 44 |  | Nam | Complete |  |  | current_emissions - (current_heat_emissions + heat_pump X square footage X building vintage / efficiency factor)
double check rounding in calculated footprint | Part 1 | Nam | Complete |  |  | testing
Fill in rest of cities for part 2 (google drive) | Part 2 | Nam | Complete |  |  | Anything less than 2 hours drive go to the nearest airport
Add new paaremeters for current gloal emissions: 3.82 | Part 1 | Nam | Complete |  |  | Now it is 6.2. Round to 3.8
Subtask: Store iterations of code in Github to track changes | All | Nam | Complete | High |  | Store all versions of code in Github to be able to track changes
Initiate refund + buy $1000 credit for piloting | All | Vivian | Complete | High |  | Refund requested, ticket submitted to change currency of new workspace
allow going backward on Survey 2 (except after disclosure script) | Part 2 | Nam | Complete | High
bots for prolific | All | Vivian | Complete |  |  | Prolific's own checks seem good, added new task below.
Turn on metadata | All | Nam | Complete
Investigate screening survey | Pre-survey | Vivian & Nam | Complete |  |  | Flying filter no longer available, we need screening survey. 4,886 Canadians,
Create screening survey | Pre-survey | Vivian & Nam | Complete |  |  | Have you flown in the last 2 years?
Get travel voucher |  | Vivian | Complete |  |  | check in with travel agent / procurement
Send vivian a copy of the part 1 survey | Part 1 | Nam | Complete |  |  | send link to vivian
move text re alternative destinations after links to examples | Part 2 | Nam | Complete | High
update calculator documentation | All | Vivian & Nam | Complete
Add clearance number | All | Vivian & Nam | Complete
Option A (Flight), Option B (Local) | Part 2 | Nam | Complete | High
Delete montreal from options for flights | Part 2 | Nam | Complete | High |  | We decided to keep montreal here
Revise consent form | All | Vivian | Complete |  |  | revised, entered into surveys, changes tracked for resubmission.
add max number of local destinations and check that they are blank if not used | Part 2 | Nam | Complete | High
Block randomize 2a/b, 3a/b, 4a/b, 5a/b | Part 2 | Nam | Complete | High
Check for any spelling errors and that it matches the most recent design sheet | Part 1 | Nam | Complete | High | 2026-06-11 | * Can partipants do this using a smartphone? If so, change consent text to reflect.
Part 2 Survey | Part 2 | Nam | Complete | High
Subtask: Add United States cities and emissions | Part 2 | Nam | Complete | High
Subtask: Go through make the code and create a readme document | All | Nam | Complete | High |  | Double check rounding for values for example
Remove Carleton logo from survey format (I've added to 2/3 consent sections - not part 2) |  | Nam | Complete | High
Do a pre-analysis plan | All | Vivian | In progress | Medium |  | Will run by Nick before submitting
Update tax regime numbers | Part 2 | Vivian | Complete | High | 2026-06-05 | Look into current numbers for carbon tax regimes, i.e., 32USD etc.
Make sure to calibrate the tax regimes for both american and canada currencies | Part 2 | Nam | Complete | High
Change 3b to how much money does your household normally spend instead of how much... | Part 1 | Nam | Complete | High
Change number 14 to which is used the most by your hosuehold and change 15 to is that car .... | Part 1 | Nam | Complete | High
Send Nick a copy of both surveys to test and get feedback | All | Nam | Complete | Low |  | let's wait until everything is working together
Add grand junction as a city | Part 2 | Nam | Complete | High | 2026-06-05 | Do the same thing for grand junction
Change state from Montana to Colorado in Part 1 survey | Part 1 | Nam | Complete | High | 2026-06-05
Add denver / any other relevant cities to list of cities in part 1 | Part 1 | Nam | Complete | High | 2026-06-05 | Question 6 of Survey part 1
Randomization of part 2 questions | Part 2 | Nam | Complete | Medium |  | Q2-5 need to be fully randomized. Can we randomize order within the block of questions?
Change short, medium, and long-haul flight questions to reflect colorado | Part 1 | Nam | Complete | High | 2026-06-05
Create a short haul flight map for denver | Part 1 | Nam | Complete | High | 2026-06-05
Switch survey currency to USD | All | Vivian | Complete | Low |  | Had to erase draft studies, escalated this to Prolific support, may cause delays as they need to issue refund first
Finalize 2 local destinations per city | Part 2 | Vivian | Complete | High
See if you can optimize for mobile | All | Nam | Complete | Low
Create a medium haul flight map for denver | Part 1 | Nam | Complete | High | 2026-06-05
Create a long haul flight map for denver | Part 1 | Nam | Complete | High | 2026-06-05
Adjust short, medium and long haul text for Colorado | Part 1 | Nam | Complete | High | 2026-06-05
Add option 2b-local | Part 2 | Nam | Complete | High | 2026-06-05 | Look at the sheet of paper that contains logic. But essentially, 2b-local should only appear for the FIRST time that the person chooses local vacation as an option.
Redo consent forms | All | Vivian | In progress | High | 2026-06-17
Add option 2c,3c,4c,5c | Part 2 | Nam | Complete | High | 2026-06-05 | Do this for every question
Make edits to parameters | Part 1 | Vivian | Complete | High | 2026-06-17
Add Tax regimes for american set | Part 2 | Nam | Complete | High | 2026-07-13
Add pueblo, grand junction, fort collins, colorado springs | Part 2 | Nam | Complete | High | 2026-06-05
Add a resort for brekenridge | Part 2 | Nam | Complete | High | 2026-06-05
Add a resort for aspen | Part 2 | Nam | Complete | High | 2026-06-05
Update short haul text for colorado | Part 2 | Nam | Complete | High | 2026-06-09
Update drop down list for pueblo, grand junction, fort collins, colorado springs | Part 2 | Nam | Complete | High | 2026-06-09
Test Part 2 | Part 2 | Nam | Complete | High | 2026-06-09 | We will have to get rid of some local destinations so that the piped text works in 2b-local. Otherwise, there are blanks that the user can choose from
Add the warning message if they aren't close enough and add the warning message if the choice is not numeric | Part 1 | Nam | Complete | High |  | Having some trouble here since qualtrics only allows one error message not two.
Change validation message | Part 1 | Nam | Complete | High | 2026-06-10 | Change error message for calculator questions
Change long haul text for Canada | Part 1 | Nam | Complete | High | 2026-06-10 | Change long haul text to Canada to Europe or Asia.
Remove montana and then add colorado | Part 2 | Nam | Complete | High |  | Need to add cities for denver , grand junction
Change the wording of the part 2 survey for local trip | Part 2 | Nam | Complete | High
Add a part c where you ask where you will go | Part 2 | Nam | Complete | High
We want to only show drive once and then fly | Part 2 | Nam | Complete | High |  | I'm not sure what this means
Change the world map | Part 1 | Nam | Complete | High
Test calculator | Part 1 | Nam | In progress | High | 2026-07-13
Integrate Qualtrics and Prolific | Pilot | Nam | Complete | Medium |  | https://www.youtube.com/watch?v=qi6oRJrD84o
Implement Prolific's bot checks and LLM checks (just for text entries at end of Survey 2) | Pilot | Nam | Complete | Medium |  | https://researcher-help.prolific.com/en/articles/445144-what-are-authenticity-checks
Part 1 Survey Double checks | Part 1 | Nam | Complete | Medium
Double check design and add questions if necessary | All | Nam | Complete | Low
Standardize spelling | Part 1 | Nam | Complete | Low |  | Kilometres vs kilometers
Double check that links | Part 1 | Nam | Complete | Low |  | links should open to new page, ie, target = _blank
Double check randomizer for unbalanced outcome | Part 2 | Nam | Complete | Low |  | Follow-up with how this is done
Change medium haul text | Part 1 | Nam | Complete | High | 2026-06-10 | Change medium haul text examples using a major city in province / state and then city on the cut off that is relatively popular / populous
Track key documents in a table of contents | All | Nam | Backlog | Low
We can use the survey as it is and we push it out separately. | [5 empty] | Do it within Qualtrics. Participants will fill out the survey and then if they check all
Write screener questions in design file | Part 1 | Vivian | Complete | High | 2026-06-10 | Add screening questions
Add prolific ID question | All | Nam | Complete | High | 2026-06-12
Check that integration works | Part 2 | Nam | Complete | High | 2026-07-13
Pilot with initial survey and then for final study we can break into batches
Write up validation message | [5 empty] | Text: Your response is off by more than 0.5, or contains non-numeric characters.
Add re-direct end of survey | All | Nam | Complete | High | 2026-06-12
Change emission factors for montana to Colorado | Part 1 | Nam & Vivian | Complete | High | 2026-06-05 | Change any relevant functions, parameters etc.
Check that validation is set for every question in part 1 | Part 1 | Nam | Complete | High | 2026-06-11
Integrate cooling and new home heating stuff | Part 1 | Nam | Complete | High | 2026-06-19
Check that prolific gives us survey duration (during pilot); add time stamps if not | All | Nam & Vivian | Complete | Medium | 2026-06-10
Modify Home enery | Part 1 | Nam | Complete | High | 2026-06-24
Change tax regimes |  | Vivian | Complete | High | 2026-06-12 | see Tax Regimes tab
make edits to code | Part 1 | Nam | Complete | High | 2026-06-17
Modify Part 2 Survey to match survey design | Part 2 | Nam | Complete | High | 2026-07-13
Draft recruitment script in Prolific | Part 1 & Rentention & Part 2 | Vivian | Complete | High |  | Included Tablet or Computer requirement for Part 1, but not Screen or Part 2 (seems to disallow bot checks?)
Change layout so that from left to right the emissions decreases | Part 1 | Nam & Vivian | Complete | High | 2026-06-18 | Did we want to make it so that the buttons from left to right so that the emissions decreases
Fix spelling mistakes in html | Part 1 | Nam | Complete | High | 2026-06-19 | remove hyphens
When no car is selected, emissions stay at zero instead of increasing | Part 1 | Nam | Complete | High | 2026-06-19
Add logic to test survey | Part 1 | Nam | Complete | Low | 2026-06-19
Swap order in radio buttons to match form | Part 1 | Nam | Complete | High | 2026-06-19
Add new design questions | Part 1 | Nam | Complete | High | 2026-06-19
Fix intro text bolding | Part 1 | Nam | Complete | High | 2026-06-24
Verify Diet Emission | Part 1 | Nam | Complete | Low | 2026-06-24
Verify Flight Emissions | Part 1 | Nam | Complete | Low | 2026-06-24
Add screener questions to Survey part 1 | Part 1 | Nam | Complete | Medium | 2026-06-10
Set up protocol to invite specific participants to subsequent surveys after screener & completion of Part 1 | Pilot | Nam | Complete | Low | 2026-06-10 | https://researcher-help.prolific.com/en/articles/445163-how-can-i-invite-specific-participants-to-my-study?_gl=1*1utogy8*_gcl_au*MTE5NzAxMjIzOS4xNzc2Nzg3MjAy
IRB revision | All | Vivian | In progress | High |  | let's wait until we finish pilot
Deleate
Figure out contact list with Qualtrics | Pilot | Nam | Complete | Very High
Update Footprint parameters to fit Qualtrics guidelines | Part 2 | Nam | Complete | Very High | 2026-07-01 | Needs to be max 30 columns
Add prolific PID to both questions | All | Nam | Complete | High | 2026-07-01 | Add to both surveys
Double check kingston destinations | Part 2 | Vivian | Complete | High | 2026-07-01 | Bruce peninsula is greater than 5 hour drive
Generate medium haul screenshots based on prompt | Part 1 | Nam | Complete | High | 2026-07-06
Change QIDs so that claude can implement in the calculator | Part 1 | Nam | Complete | High | 2026-07-08
Generate short haul screenshots based on prompt | Part 1 | Nam | Complete | High | 2026-07-09
Add new question to part 1 | Part 1 | Nam | Complete | High | 2026-07-09
Add guam, puerto rico, and the US virgin islands to the list of states in the survey. | Part 1 | Nam | Complete | High | 2026-07-09
Add us territories to list of for part 2 survey. | Part 2 | Nam | Complete | High | 2026-07-09
Add short haul flights graphics into the survey | Part 1 | Nam | Complete | High | 2026-07-10
updates carbon calculator | Part 1 | Nam | Complete | High | 2026-07-11
add medium haul flights into the survey | Part 1 | Nam | Complete | High | 2026-07-11
Change the embedded values | Part 1 | Nam | Complete | High | 2026-07-09 | short-distance for canada to 480km, for origin country, continental usa
Convert kgs to tons | Part 2 | Nam | Complete | High | 2026-07-07 | Convert co2e to t instead of kg
Add closest airport city for Canadian set | Part 2 | Nam | Complete | High | 2026-07-10
Add closest airport city for American set | Part 2 | Nam | Complete | High | 2026-07-09
remove the number of people and see how IRB responds | All | Vivian | To do | High
Look into geolocation for the survey (zip codes for example) | Part 1 | Vivian | Complete | Medium
Change attention check number 12 | Part 1 | Vivian | To do | High
Misunderstanding placeholder question | Part 1 | Vivian | To do | High | 2026-06-24
Add Guam, puerto rico, and the US virgin islands to spreadsheets. | Part 2 | Nam | Complete | High | 2026-07-13
Investigate randomization order workflow | Part 1 | Nam & Vivian | Complete | High | 2026-07-13 | Look into prerandomized list in prolific and qualtrics.
Look into donut shaped maps for medium haul. | Part 1 | Nam | Complete | High | 2026-07-15
Randomize order for actions | Part 1 |  | Complete | High | 2026-07-15
Revise question 32 | Part 1 | Vivian | To do | High | 2026-07-15
Look at the benchmark numers | Part 1 | Vivian | Complete | High | 2026-07-15
Look at closest city as opposed to closest international airport | Part 2 | Nam & Vivian | Complete | High | 2026-07-15
Verify randomization | Part 1 |  | Complete | High | 2026-07-15
Look at consent for forced responses | All | Nam & Vivian | Complete | High | 2026-07-15
Add question to part 2 | Part 2 | Nam | In progress | High | 2026-07-22
Fix global target to 1.57 | Part 1 | Nam | Complete | High | 2026-07-15
Integrate Puerto Rico and Virgin Islands | Part 1 | Nam | Complete | High | 2026-07-20
ethical approval, nick, and the analysis plan | All | Vivian | To do | High | 2026-07-20
Implement randomization scheme |  |  |  |  | 2026-07-20
Implement all randomizations | All | Nam | Complete | High | 2026-07-20
Change surveys to match new design | All | Nam | Complete | High | 2026-07-21
Add heat pump question to calculator | Part 1 | Nam | Complete | High | 2026-07-21
Transplant income brackets from integration | Part 1 | Nam | Complete | High | 2026-07-22
Code attention checks | All | Nam & Vivian | To do | High | 2026-07-15
Change questions to lower resolution png | Part 1 | Nam | Complete | High | 2026-07-22 | Try to use claude to add pictures into
Figure out if I can connect claude to qualtrics | Claude | Nam | In progress | High | 2026-07-22
Investigate shared claude code workspaces | Claude | Nam | In progress | High | 2026-07-22
Add code to VI, and PR jurisdictions. | Part 1 | Nam | In progress | High | 2026-07-22
Add code to back up heat pump calculations. | Part 1 | Nam | In progress | High | 2026-07-22 | These can be found in the claude input.
Modify flight and local destination questions | Part 1 | Nam | In progress | High | 2026-07-24
Find list of emails for Zip codes and fsa of MPs and congresspeople | Claude | Nam | In progress | High | 2026-07-24 | Can't see their names, but we need a way to see that they sent it, and their prolific id. And sending an email to those people.
Add display logic for questions
Note on A103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added the logo to part 2
Note on G124: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What question type did we want here?

## Survey Design Progression
Date | Details | Number of people surveyed
2026-05-01 | Integrating Qualtrics and Prolific. Technical errors with consent portion. | 1

## Prolific Pilot Log
Pilot ID | Date | Details | Number of people surveyed
1 | Jul 16 - Jul 18 | Integrating Qualtrics and Prolific. Technical errors with consent portion. | 1
2

## Calendar
July | [5 empty] | 2026
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
29 | 30 | 1 | 2 | 3 | 4 | 5
6 | 7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 22 | 23 | 24 | 25 | 26
27 | 28 | 29 | 30 | 31 | 1 | 2
3 | 4 | Notes:
August | [5 empty] | 2026
MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY | SUNDAY
27 | 28 | 29 | 30 | 31 | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
Vivian Vacation
10 | 11 | 12 | 13 | 14 | 15 | 16
Vivian Vacation
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30
31 | 1 | Notes:

## Prolific list of issues
1. Declined to consent | consent needs to be carefully crafted
2

## Important Notes
Description | Explanation | Notes
I used the following formula to round numbers to 2 significant figures ROUND(U2*#REF!$D$2, 1 - INT(LOG10(ABS(U2*#REF!$D$2)))) | Round takes two arguments: number, and number of digits to round. 1) We pass the carbon emissions * carbon tax regime as the first argument. 2) We pass an equation that finds the leading digit. | See this answer on using claude fable: https://claude.ai/share/5f2373d6-965e-4053-865d-d9c0bb182516
Anyone choose local?

## Documentation Table of Contents
Location | Folders | Document Name | Description | Link
Dropbox | Design | Design | This is the most up-to-date experimental design which contains all of the
Github |  | Carbon Calculator Code | This is where all the code for the carbon calculator lives. I'm also going to add any code that we've used in any of the surveys here. | https://github.com/nam-chu-2/icureus_carbon_calculator

## Bug Log
Date | Issue | Status | Step-by-step
2026-05-05 | Recode | Resolved | Values needed to be recoded in the part 1 survey
2026-06-19 | Calculator | Debugging | When car is selected, emissions doesn't simulate user driving 17,000 kilos

## Drop down stuff
Status | Survey | Assignees | Urgency
To do | Part 1 | Vivian | High
In progress | Part 2 | Nam | Medium
Complete | Retention | Vivian & Nam | Low
Vivian to review | Pre-survey |  | Very High
Backlog | All
Debugging | Pilot
Claude

## Pilot checklist (hidden)
survey number | question number | question | validation | min/max | display logic
1 | 0 | consent | no |  | end
1 | 0 | In what country do you live? | no
| 1 | in what year were you born? | yes | 1920/2008
| 2 | What is your gender? | no
| 2t | What do you know better: your pre-tax or post-tax annual income? | no
| 3-pretax | What is your household's pretax income? | no
| 4-posttax | what is your household's posttax income? | no
| 4-province | In what province do you live? | no |  | Canada selected
| 4-state | In what state do you live? | no |  | USA selected
| 5 | education | no
| 6 | Major metro area | no
| 7 | How long does it take to drive? | no
| 8 | largest city of town | no
| 9 | lots of things do to | no
| 10 | lots of places to explore | no
| 11a | children
| 11b | passport
|  | flights |  | min: 0

## Survey Feedback
Date | Person | Feedback
Dec. 29, 2025 | Carlos | What is your gender: maybe male female instead of man woman
What is your highest level of education: did a three year degree so picked the third option
How long does it take to drive to this city: since he lives in ottawa, he sees this as "how long does it take to drive from where I am to downtown".
short haul flights: Carlos incorporated his layovers in this - technically if one goes to calgary sometimes they will have to stop at toronto
How many kids: change to drop down
How much does your actions contribute to climate change depends on your lifestyle.
Some grammar mistakes
2026-06-18 | Eloisa | I will take the tokyo trip regardless since the experiment is free